## WEST DES MOINES, IA Shot Schedu
Prio | VIDEO ID | Line Segment | LOCATION | END SEAL TO USE | US MH | USMH Depth | Prep USMH Depth | DS MH | DSMH Depth | Prep DSMH Depth | Pipe Size | Prep Crew Verified Dia | Mill Thickness | Map Length | Shot Length | Services | Ready to Line - Certified by Prep Crew Lead | Prep Crew | Prep Date | Easement | Traffic Control | Special Notification Requirements | Water Flow % | Prep Roller Tape FT | TV Prep Footage | Est Active Taps | Est Inactive Taps | Prep Remove Protruding Tap (IRON)-EA | Prep Remove Protruding Tap (NOT IRON)- EA | Heavy Cleaning FT | Prep Heavy Clean-Hours | Prep Rootsawing FT | Prep Rootsaw Hours | Prep Lumberjack FT | LJ Hours | IST HOURS | Feet of PVC Main | Dropper Info: Int or Ext & Ft | Prep Complete | Wet Out | Reefer | Lining Date | CIPP Superintendent | Cutter Operator | Preliner Installed FT | Installed Liner FT | DIAMETER | Reinstated Services | Reinstated Droppers | Removed Protruding Taps (IRON) -EA | Removed Protruding Taps-(non Iron)-EA | Rootsawing FT | Rootsaw HRS | Lumberjack FT | Lumberjack HRS | CIPP Labor HRS | Post TV | Final Post TV Date | Post TV Video Rcvd | Pre TV Video Rcvd | Diam on Post TV | LINER LOT # | Video Line Segment Footage | Video Line Segment Service Count | Lining Issues | Post - CIPP Crew FT Diff Check | Grout State Date | Grout Superintendent | # of Grout Tests | # of Grout Seals | Gallons of Grout | Grout Labor Hrs | Rcvd Pre-Grout Video | Reviewed Post-Grout Video | Grout Report # | Live Grout Lateral | Capped Grout Laterl | Failed Grout Joints | Passed Grout Joints | Failed Grout Lateral | Unable to Grout Lateral | Unable to Grout Joints | Passed Lateral | Total Gallons | Grout Length Surveyed | Grouting Issues | % Done | Predecessors
| 0.01 | SUMMARY SHEET | IT PIPES DATABASE TO SYNCH TO: | FIRST THING, FIND ALL THE MANHOLES FIRST AND LET KALEB KNOW IF ANY ARE MISSING. 11/19- All MH Located, Stephen B | ENGINEERING WEBSITE, UTILITIES AND IT WILL HAVE YOUR LOCATION AND THE MANHOLE YOU ARE LOOKING FOR | CAN USE BIKE TRAILS CAN'T USE FOR JET AND HIGHER. 2 TIRES IN THE MIDDLE OF IT ARE OK. |  |  | CURE LOGS NEED TO BE TURNED IN. |  |  |  | Totals: | 4222 | 4535 | 2 | [7 empty] | Totals: | 1647 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Totals: | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Totals: |  | 0 | 0 |  | 0 |  | Totals: | 0 | 0 | 0 | 0
| 0.02 | flow level per TV | DO NOT USE LUMBERJACK CHAINS IN THE LINES | Trails shall be closed while work is being performed. | 12. Contact the West Des Moines Parks Department (Marco Alvarez - 515-222-3452) a minimum of seven (7) days prior to working near or closing a trail. | EITHER STAY ON THE TRAIL OR STAY OFF IT COMPLETELY.
| 1 | 11323 |  | INSIGNIA | 09-016 | 4.5 | 4.6 | 09-015 | 4.5 | 16 | 8 | 8 |  | 14 | 14 | 1 | TRUE | Stephen B | 2025-11-20 |  |  |  | 5% | 13 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EXT 5 FT | TRUE | [26 empty] | 0
| 2 | 10922 |  | INSIGNIA | 09-051 | 6.8 | 6.11 | 09-015 | 4.5 | 16 | 15 | 15 |  | 314 | 313 | 0 | TRUE | Stephen B | 2025-11-20 | TRUE |  |  | 10% | 314 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [26 empty] | 0
| 3 | 11324 |  | INSIGNIA | 09-015 | 16.2 | 16 | 09-014 | 16.2 | 14.7 | 15 | 15 |  | 244 | 558 | 0 | TRUE | Stephen B | 2025-11-20 | TRUE |  |  | 10% | 244 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [26 empty] | 0
| 4 | 11325 |  | INSIGNIA | 09-014 | 14.1 | 14.7 | 09-013 | 14.1 | 14.11 | 15 | 15 |  | 156 | 156 | 1 | TRUE | Stephen B | 2025-11-20 | TRUE |  |  | 10% | 153 | 153 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [26 empty] | 0
| 5 | 11327 |  | INSIGNIA | 09-012 | 11.2 | 11.4 | 09-011 | 11.2 | 8.11 | 15 | 15 |  | 285 |  | 0 | TRUE | Stephen b | 2025-11-20 | TRUE |  |  | 10% | 284 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [26 empty] | 0
| 6 | 12462 |  | INSIGNIA | 09-011 | 9 | 8.11 | 09-010 | 9 | 8.8 | 15 | 15 |  | 269 |  | 0 | TRUE | Stephen b | 2025-11-20 | TRUE |  |  | 5% | 266 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [26 empty] | 0
| 7 | 11336 |  | INSIGNIA | 09-010 | 8.7 | 8.8 | 09-009 | 8.7 | 9.3 | 15 |  |  | 226 |  | 0 |  |  |  | TRUE | [45 empty] | 0
| 8 | 11340 |  | INSIGNIA | 09-009 | 7.2 | 9.3 | 09-008 | 7.2 | 6.4 | 15 |  |  | 291 | 1071 | 0 |  |  |  | TRUE | [45 empty] | 0
| 9 | 11328 |  | INSIGNIA | 09-061 | 12.8 | 12.11 | 09-060 | 12.8 | 12.2 | 18 | 18 |  | 380 |  | 0 | TRUE | Stephen B | 2025-11-20 | TRUE |  |  | 5% | 378 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | [26 empty] | 0
| 10 | 11334 |  | INSIGNIA | 09-060 | 12.3 | 12.2 | 09-082 | 12.3 | 12.7 | 18 | 18 |  | 34 |  | 0 | TRUE |  |  | TRUE
| 11 | 11335 |  | INSIGNIA | 09-082 | 12.8 | 12.7 | 09-087 | 12.8 | 14 | 18 |  |  | 309 |  | 0 |  |  |  | TRUE | [45 empty] | 0
| 12 | 11337 |  | INSIGNIA | 09-087 | 14.1 | 14 | 09-059 | 14.1 | 14.9 | 18 |  |  | 60 |  | 0 |  |  |  | TRUE | [45 empty] | 0
| 13 | 11341 |  | INSIGNIA | 09-059 | 14.5 | 14.9 | 09-058 | 14.5 | 12.2 | 18 |  |  | 134 | 917 | 0 |  |  |  | TRUE | [45 empty] | 0
| 14 | 11344 |  | INSIGNIA | 09-007 | 9.9 | 10.2 | 09-006 | 9.9 | 6.11 | 15 |  |  | 390 |  | 0 |  |  |  | TRUE | [45 empty] | 0
| 15 | 11346 | 20 feet of Pipe 11346 turbulation. High pressure cleaning maybe needed. contact AE if needed. | INSIGNIA | 09-006 | 6.8 | 6.11 | 09-005 | 6.8 | 7.8 | 15 |  |  | 302 |  | 0 |  |  |  | TRUE | [17 empty] | INT 7 FT | [27 empty] | 0
| 16 | 11347 |  | INSIGNIA | 09-005 | 7.6 | 7.8 | 09-004 | 7.6 | 15.3 | 15 |  |  | 130 | 822 | 0 |  |  |  | TRUE | [45 empty] | 0
| 17 | 17666 |  | INSIGNIA | 09-058 | 12 | 12.2 | 09-057A | 12 | 14 | 21 | 21 |  | 87 |  | 0 |  |  |  | TRUE |  |  |  | 89 | [41 empty] | 0
| 18 | 11342 |  | INSIGNIA | 09-057A | 13.3 | 14 | 09-057 | 13.3 | 14 | 21 | 21 |  | 158 |  | 0 |  |  |  | TRUE |  |  |  | 161 | [41 empty] | 0
| 19 | 11345 |  | INSIGNIA | 09-057 | 14.1 | 14 | 09-056 | 14.1 | 11 | 21 | 21 |  | 402 | 647 | 0 |  |  |  | TRUE |  |  |  | 410 | [41 empty] | 0
| 20 | 12308 | 12308 extends too far into Manhole 09-004. Trim pipe to within 3 inches of the manhole wall. Also grout/mortar space between parallel pipes in this manhole to smooth area and cut down on turbulence. | INSIGNIA | 09-055 | 11.9 | 12.1 | 09-004 | 11.9 | 15.3 | 21 | 21 |  | 37 | 37 | 0 |  |  |  | TRUE |  |  |  | 39 | [41 empty] | 0
| 20 | {FDEA1F5D-1A01-4834-B049-D2C798D0D52E}.png | [63 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
2025-11-20